## RUData
Workstream | TaskRelatedTo | Task Type | Task | Requestor | Status | Date | Emp Name | Total Minutes Worked
Tagging | Web | Cards | Migrated Reddit All Cards pixel | Raymond Dolan | Completed | 2026-10-21 | Rajavel
Tagging | Web | Cards | Migrated Meta Travel Portal pixel | Raymond Dolan | Completed | 2026-10-21 | Rajavel
Tagging | Web | Cards | Migrated DoubleClick AA Globe pixel | Raymond Dolan | Completed | 2026-10-22 | Rajavel
Tagging | Web | Cards | Migrated DoubleClick AA Airport OOH pixel | Raymond Dolan | Completed | 2026-10-22 | Rajavel
Tagging | Web | Cards | Migrated Acxiom AA Platinum pixel | Raymond Dolan | Completed | 2026-10-22 | Rajavel
Tagging | Web | Cards | Migrated DoubleClick AA Business pixel | Raymond Dolan | Completed | 2026-10-23 | Rajavel
Tagging | Web | Cards | Reviewed YouTube and Google Ads pixel migrations | Raymond Dolan | Completed | 2026-10-23 | Rajavel
Tagging | Web | Cards | Reviewed Bing remarketing pixel conditions | Raymond Dolan | Completed | 2026-10-23 | Rajavel

## Task- Tracker
Sr. No. | Work Stream | Task Name | Task Type | Requestor | Task Owner | Status | Request Date | Start Date | Target Delivery Date | Actual Delivery Date | Remarks | Week
1 | Tagging | Reddit All Cards Landing Page Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | Completed |  | 2026-10-21 |  | 2026-10-21 | 21-Oct-2026: Implemented the Reddit All Cards pixel in Adobe Launch. Migrated its supported URL eligibility conditions and the vendor tracking configuration. Ensighten: P1T_Cards_Reddit_AllCards_LandingPage_March2026 Adobe Launch: Third_Party_Cards_Reddit_AllCards_LandingPage Completion refers to Launch implementation. | 2026-10-19
2 | Tagging | Meta Travel Portal Login Landing Page Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | Completed |  | 2026-10-21 |  | 2026-10-21 | 21-Oct-2026: Implemented the Meta Travel Portal pixel in Adobe Launch, including its applicable hostname, path and protocol conditions and the existing Meta tracking behavior. Ensighten: P1T_Cards_Meta_TravelPortal_LoginLandingPage_April2026 Adobe Launch: Third_Party_Meta_Cards_TravelPortal_LoginLandingPage Completion refers to Launch implementation. | 2026-10-19
3 | Tagging | DoubleClick AA Globe Landing Page Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | Completed |  | 2026-10-22 |  | 2026-10-22 | 22-Oct-2026: Implemented the AA Globe Floodlight configuration. Reviewed its production and UAT URL eligibility and mapped the existing Floodlight activity configuration. Ensighten: P1T_Cards_DoubleClick_AAGlobe_LandingPage_September2025 Adobe Launch: Third_Party_Cards_DoubleClick_AAGlobe_LandingPage Completion refers to Launch implementation. | 2026-10-19
4 | Tagging | DoubleClick AA Airport OOH Landing Page Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | Completed |  | 2026-10-22 |  | 2026-10-22 | 22-Oct-2026: Implemented the AA Airport OOH Floodlight configuration. Reviewed the URL-matching conditions and corresponding Floodlight activity parameters. Ensighten: P1T_Cards_DoubleClick_AAAirportOOH_LandingPage_September2025 Adobe Launch: Third_Party_Cards_DoubleClick_AAAirportOOH_LandingPage Completion refers to Launch implementation. | 2026-10-19
5 | Tagging | Acxiom rTag AA Platinum Landing Page Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | Completed |  | 2026-10-22 |  | 2026-10-22 | 22-Oct-2026: Implemented the Acxiom rTag AA Platinum landing-page configuration and reproduced the two applicable page-path conditions. Reviewed the request parameters used by the existing implementation. Ensighten: P1T_Cards_Acxiom_rTag_AAPlatinum_LandingPage_August2025 Adobe Launch: Third_Party_Cards_Acxiom_rTag_AAPlatinum_LandingPage Completion refers to Launch implementation. | 2026-10-19
6 | Tagging | DoubleClick AA Business Landing Page Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | Completed |  | 2026-10-23 |  | 2026-10-23 | 23-Oct-2026: Implemented the AA Business Floodlight conversion rule, including URL eligibility, Floodlight activity mapping, transaction-counting configuration and the required custom parameters. Ensighten: P1T_Cards_DoubleClick_Conversion_AABusinessLandingPage_April2021 Adobe Launch: Third_Party_Cards_DoubleClick_Conversion_AABusinessLandingPage Completion refers to Launch implementation. | 2026-10-19
7 | Tagging | YouTube SMB Conversion Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | WIP |  |  |  |  | Reviewed the existing YouTube/Google Ads tracking configuration, conversion IDs and labels, Google tag conversion tracking and the available YouTube video-tracking extension. Further implementation or validation is pending. Ensighten: P1T_Cards_Youtube_Conversion_SMB_July2020 | 2026-10-19
8 | Tagging | YouTube Elite Landing Page Conversion Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | WIP |  |  |  |  | Reviewed the existing YouTube/Google Ads tracking configuration, conversion IDs and labels, Google tag conversion tracking and the available YouTube video-tracking extension. Further implementation or validation is pending. Ensighten: P1T_Cards_Youtube_Conversion_EliteLandingPage_2887_Feb2022 | 2026-10-19
9 | Tagging | YouTube AA SMB Conversion Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | WIP |  |  |  |  | Reviewed the existing YouTube/Google Ads tracking configuration, conversion IDs and labels, Google tag conversion tracking and the available YouTube video-tracking extension. Further implementation or validation is pending. Ensighten: P1T_Cards_Youtube_Conversion_AASMB_2888_Feb2022 | 2026-10-19
10 | Tagging | YouTube AA MileUp Conversion Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | WIP |  |  |  |  | Reviewed the existing YouTube/Google Ads tracking configuration, conversion IDs and labels, Google tag conversion tracking and the available YouTube video-tracking extension. Further implementation or validation is pending. Ensighten: P1T_Cards_Youtube_Conversion_AAMileUp_2889_Feb2022 | 2026-10-19
11 | Tagging | YouTube AA Consumer Committed Pixel Migration | Core Deliverables | Raymond Dolan | Rajavel | WIP |  |  |  |  | Reviewed the existing YouTube/Google Ads tracking configuration, conversion IDs and labels, Google tag conversion tracking and the available YouTube video-tracking extension. Further implementation or validation is pending. Ensighten: P1T_Cards_Youtube_AAConsumerCommitted_July2020 | 2026-10-19
12 | Tagging | YouTube and Google Ads Pixel Migration Review | Core Deliverables | Raymond Dolan | Rajavel | Completed |  | 2026-10-23 |  | 2026-10-23 | 23-Oct-2026: Reviewed legacy Google Ads conversion tracking, gtag.js migration, conversion IDs and labels, and the suitability of the Adobe Launch YouTube video-tracking extension. Completed the review activity only. The five YouTube/Google Ads migration implementations remain WIP. | 2026-10-19
13 | Tagging | Bing Cards Invitation Remarketing Rule Review | Core Deliverables | Raymond Dolan | Rajavel | Completed |  | 2026-10-23 |  | 2026-10-23 | 23-Oct-2026: Compared the existing Bing Cards Invitation remarketing rule conditions against the corresponding Ensighten URL criteria. Identified additional campaign combinations requiring inclusion for condition parity. Follow-up implementation and validation remain pending. Completed the review activity only. | 2026-10-19

## List
Workstream | TaskRelatedTo | Task | Status
Web Analytics | Web | CRS | WIP
Modelling Analytics | Mobile | Cards | Completed
Tagging | Others | Meeting
Segmentation |  | Retail
CRO |  | Training
CRO Developer |  | Lending
All